## Issues Summary
Issue # | Title | Severity | Current State | Target | Financial Impact | Priority
1 | Low Overall Claim Approval Rate | HIGH | 50.9% | >70% | SAR 2,906,147.86 | HIGH
2 | Excessive Partial Approvals - Revenue Leakage | HIGH | 36.2% (3,568 claims) | <15% | SAR 1,148,707.23 retained by payers | HIGH
3 | High-Value Claim Rejections | CRITICAL | 44 claims | 0 claims | SAR 927,691.52 at risk | CRITICAL
4 | Excessive Zero-Value Payment Bundles | HIGH | 91.4% (393 bundles) | <20% | Delayed cash flow, reconciliation overhead | HIGH
5 | Eligibility Check System Failure | CRITICAL | 99.9% failure rate | <10% | Service delivery without coverage verification, denial risk | CRITICAL
6 | Excessive Communication Back-and-Forth | MEDIUM | Avg 1.6 communications/transaction, Max 12 | <2 communications/transaction | Processing delays, staff time waste | MEDIUM

## Action Items
Issue # | Solution | Priority | Timeline | Expected Impact | Status | Owner | Notes
1 | Implement Pre-Submission Validation System | HIGH | 2-4 weeks | +15-20% approval rate | Not Started
1 | Insurer-Specific Submission Guidelines | HIGH | 3-6 weeks | +10-15% approval rate | Not Started
1 | Enhanced Staff Training Program | MEDIUM | Ongoing | +5-10% approval rate | Not Started
2 | Implement Partial Approval Review Process | HIGH | 1-2 weeks | Recover 20-30% of partial shortfalls | Not Started
2 | Service Bundling Optimization | MEDIUM | 4-6 weeks | -10-15% partial rate | Not Started
2 | Clinical Documentation Improvement (CDI) | MEDIUM | 2-3 months | +10-15% recovery on partials | Not Started
3 | High-Value Claim Task Force | CRITICAL | Immediate | Recover 40-60% of rejected amount | Not Started
3 | Mandatory Prior Authorization for High-Value Services | HIGH | 2-3 weeks | Prevent 80%+ future high-value rejections | Not Started
4 | Payment Reconciliation Process Overhaul | HIGH | 3-4 weeks | Reduce zero bundles to <20% | Not Started
4 | Payer Follow-Up Campaign | MEDIUM | 2-4 weeks | Collect pending amounts | Not Started
5 | Emergency NPHIES Integration Fix | CRITICAL | 1-2 weeks (URGENT) | Restore eligibility checks to >90% success | Not Started
5 | Patient Identifier Validation | HIGH | 1-2 weeks | Prevent 30-40% of format-related errors | Not Started
5 | Manual Verification Backup Process | HIGH | Immediate | Prevent service delivery without coverage | Not Started
6 | First-Time-Right Submission Initiative | MEDIUM | 4-6 weeks | Reduce communications by 40-50% | Not Started
6 | Automated Response Templates | LOW | 2-3 weeks | Reduce response time by 50% | Not Started